## Century Coordination Tasks
Task Description | Area | Timing (no later than) | Volunteer Description | 2016 Volunteers | 2016 Status | Notes
Determine Date and Start Point for Century | Century Coordination | January |  | RBC Board | Complete | Date: August 28, 2016 Start and End Point Reston Town Center
Determine Routes | Route Development | February |  | Bobby/Ken/Chip | Complete | Determine route/route changes for Half Metric, Metric and Century
Submit WO&D Application and Approval | Route Approval | March |  | Ken | Complete | Ken will submit once route is known
Route Approval | Route Approval | March |  | Chip | In Progress | Submit form to Loudon County (online form) Coordinate with: VDOT (if on road and no roads closed its OK) Loudon County Sherriff's office Town of Leesburg - Ken is filling out the form for Leesburg Town of Middleburg Town of Purciville Herdon Karen to look for information to provide Chip for this
Permission for Rest Stops | Route Approval | March |  | Ken | Complete | Reston Town Center - complete Ashburn - complete Velo Classique - Complete Lovettsville Community Center - Complete Loudon County Mill (Old Mill) - Complete Town of Hamilton: Lori Jones (Hamilton Community Center) - Complete
Determine Volunteers needed | Volunteer Coordination | February |  | Karen Palino | Complete | Based on this list and the volunteers needed right at the century
Request Volunteers (Pre-Century) | Volunteer Coordination | February |  | Karen Palino | In Progress | On the Website and on Sign-up Genius http://www.signupgenius.com/go/20f0a45acaf22aafe3-2015 RestonBikeClubVolunteer@gmail.com RBC2015Century
Determine Volunteer incentives | Century Coordination | April |  | Board | Complete | Ideas: Comp membership and t-shirt; Get Boy Scouts and Girls Scouts to help for donation
Request Volunteers (Century and Post Century) | Volunteer Coordination | June |  | Karen Palino | Not Started | On the Website and on Sign-up Genius
Confirm Volunteers (Century and Post Century) | Volunteer Coordination | August |  |  |  | On the Website and on Sign-up Genius
Open Century Registration | Century Coordination | April |  | Ed | Complete | On the Website
Coordinate Police Assistance: with VA State Police for Century | Police Coordination | April |  | Bobby | In Progress | Past Police presence: o Belmont Ridge: 7:00 AM to Noon. This is two officers as the turns are half a mile apart and no view of each other. o Hamilton: Rest stop hours o Route / Hillsboro: Round Hill Rest Stop opening time to 30 minutes past closing. In past have had agreement in writing. 2015 we had no police presence, probably needed to start earlier and have follow-up.
Order Route Signage: if needed | Route Marking | July |  | Chip | Not Started | o Additional 12” X 18” signage if necessary. Always used FASTSIGNS and they have our artwork. They can modify if necessary. The know us as Reston Bike Club o Contact:  Sarah Manns, FASTSIGNS of Dulles, 13968 Park Center Road, Herndon, VA 20171, 703.435.8807  Process is Direct Print on Coroplast 3mm, Grommets top and bottom centered. Color: Text = Black on Grey, Arrows = Red/Blue/Yellow as required.
Inventory Route Signage: and organize for routes | Route Marking | July |  | Chip | In Progress | o Signs need to be pulled from storage roughly a month before the ride to organize for each route. Placement is basically common sense but generally:  Right Turns = 1 sign  Left Turns = 2 signs one preceding the other.  Straights = used to clarify at major intersections and long periods of no turns.  Sign install kits are in orange Home Depot bags in storage  Check kits for: • Plastic tie-offs • Pliers (for cutting ties) • Hammer • Large nail for placing wire frames in compacted road sides
Inventory Route Marking Paint: (Check supply) | Route Marking | July |  | Chip | In progress and need to order paint |  Paint can be purchased in bulk from: • AERVOE • 800-227-0196 • http://aervoe.com/paints_coatings/Marking-Chalk.html • Allow 1 to 2 weeks for delivery as it can only be shipped ground.  Markings: • Should be kept to a minimum size, clear and practiced with the teams prior to going out.
Recruit Road Marking Volunteers | Route Marking | Day before |  | Website and everyon | In Progress |  Preferably 6 teams of 2, a driver and a marker.  Depending on the routing, teams should be organized for efficiency, IE; • Reston to Ashburn Rest Stop + return (Yellow / Blue / Red) • Half metric loop (Red) • Ashburn Rest Stop to Leesburg + return (Yellow / Blue) • Leesburg to Hamilton + return from century / metric juncture (Yellow / Blue) • Hamilton to return juncture with century loop (Yellow / Blue) • Hamilton to return juncture with metric loop (Yellow)  You get the idea, it wall change a bit every year as the routes change.  Have rest stop heads place signs specific to each rest stop, they are larger 18´ X 24´signs.
Route maintenance | Route Marking | Day of |  |  | Not Assigned |  Day of, person in charge has to be available address route issues, usually based out of Hamilton.  Have signs picked up on the last drive by the sag folks Does this need more than one person, can it be shared with another role
Post Century Rider Survey | Century Coordination | Day after |  |  | Not assigned
Recruit SAG Volunteers | SAG | July |  |  | Not assigned
Coordinate SAG Volunteers | SAG | August |  |  | Not assigned
Inventory Rest Stop Bins | Rest Stop Coordination | July - early |  |  | Not assigned
Shop for Rest Stop Stock Items | Rest Stop Coordination | July - mid |  |  | Not assigned
Pack Rest Stop Boxes | Rest Stop Coordination | July - late |  |  | Not Assigned
Order Catering for RTC | Rest Stop Coordination | August |  |  | Not assigned
Order Vans for Rest Stop Distribution | Rest Stop Coordination | August - early |  | Ed | Complete
Coordinate with Reston Town Center | Rest Stop Coordination | August |  | Ken | In Progress | Had preliminary session
Shop for Rest Stop Food Items and Distribute | Century Weekend Prep | Friday before | At least 3 volunteers needed |  | Not assigned | Involves Van pickup; Shopping at Costco and Distributing items to the Town Center
Pick up Rental Vans | Century Weekend Prep | Saturday before |  |  | Not assigned
T-shirt Design | T-shirt | June |  |  | Not assigned
Determine T-shirt Color | T-shirt | July |  | RBC Board | Not assigned
Order T-shirts | T-shirt | July |  |  | Not assigned
Setup T-shirt Distribution | Century Weekend Prep | Saturday before |  |  | Not assigned
Clean up Reston Town Center | Clean up Team | Day of |  |  | Not Assigned
Clean up Storage Lockers | Clean up Team | Day of |  |  | Not assigned
Return Vans | Clean up Team | Day of
Distribute left over food | Clean up Team | Day of
Lessons Learned |  | September |  | RBC Board/Volunteers

## Volunteer Shifts
Volunteer Rest Stop or type | Shift | Date | Start | End | Hours | Number needed | Notes
Ashburn (7 - 4:30) | Setup | Sunday | 6:30am | 11:00am | 4.5 | 6
Ashburn (7 - 4:30) | Man Stop | Sunday | 10:30am | 3:00pm | 4.5 | 6
Ashburn (7 - 4:30) | Breakdown | Sunday | 2:30pm | 6:30pm | 4 | 6 | Breakdown and bring back to RTC
Hamilton (7:30 - 1:00) | Setup | Sunday | 7:00AM | 11:00am | 4 | 8
Hamilton (7:30 - 1:00) | Breakdown | Sunday | 10:00AM | 2:00PM | 4 | 6
Lovettsville (8:30 - 2:30) | Setup | Sunday | 8:00 | 12:00PM | 4 | 5
Lovettsville (8:30 - 2:30) | Breakdown | Sunday | 11:00AM | 3:00PM | 4 | 5
Old Mill (9:00 - 3:30) | Setup | Sunday | 9:00AM | 1:00PM | 4 | 5
Old Mill (9:00 - 3:30) | Breakdown | Sunday | 12:00PM | 4:00PM | 4 | 5
Round Hill?Purceville | [5 empty] | 5
Town Center | Setup/Checkin | Sunday | 6:00AM | 10:00AM | 4 | 8 | Need 6 - 8 for checkin and setup
Town Center | Lunch/T-shirts | Sunday | 10:00AM | 12:00PM | 2 | 3
Town Center | Lunch/T-shirts | Sunday | 12:00PM | 5:00PM | 4 | 5
Town Center | Cleanup/Load Vans | Sunday | 4:00PM | 8:00PM | 4 | 5
Load Vans from Storage | Pre Century | Saturday | 1:00Pm | 5:00PM | 4 | 8 | at least 6
Off Load Vans | Post Century | Sunday | 5:00PM | 8:00PM | 3 | 8
Leftover food to shelter | Post Century | Sunday | 5:00PM | 7:00PM | 2 | 2 | at least 1
Organize Storage | Post Century | Sunday | 5:00PM | 8:00PM | 3 | 2
Pick up Vans/Shop CostCo | Pre Century | Friday | 12:00PM | 4:00PM | 4 | 4
Route Marking | Pre Century | Saturday | 9:00AM | 3:00PM | 6 | 12
Route Marking Coordination | Pre Century | Saturday | 9:00AM | 3:00PM | 2
SAG
Ideas tohelp get volunteers
Comp membership and a t-shirt
Girls Scout or Boys Scout troops helping with adults at rest stops to raise money (Erin will check if some want to help at Lovettesville)
Volunteer Match
Pay movers or others

## Route Approval
Item | Instructions | Contact
Notify Loudon County of Event and route | Use the online event form at: https://www.loudoun.gov/events, you will have to attach the route. We do not need permits from VDOT unless we want to close roads. They will send contacts for other jursidictions in Loudon County
• Lovettsville Recreation Center: | Ken contacted last year
Town of Purcellville | o Send copy of the full and metric routes with dates as soon as the routes are finalized | o Contact Kitty Dugay with Purcellville Police Department, kdugay@purcellvilleva.gov
Hamilton | Last year Ken sent a letter
Leesburg | Ken sent an application last yearo Permits and Applications (last year’s attached): http://www.leesburgva.gov/government/departments/parks-recreation/festivals-community-events/permits-and-applications o Requires current certificate of insurance from Ken | o Contacts:  specevnts@leesburgva.gov • 703-777-1368  Jeremy Payne JPayne@LEESBURGVA.GOV Recreation & Events Manager Town of Leesburg Phone: 703-737-7151 Fax: 703-737-7165
Round Hill Fire Station | Rest stop permission
Herndon | Last year I only got an email that all was good for Herndon. In past years A Memorandum of Understanding Was generated by the Town for us to sign. There is a road use permit that we were supposed to submit and I did that today. They will let us know within 10 days if approved. I will follow-up tomorrow as there is a 30 day before deadline so I want to make sure they received it. I spoke with Sargent Bobby Galpin in Herndon and he may need more information. | Jean Diggs; Michelle Flores in Herndon.
Loudon Mill | Rest stop permission | karen@loudounmillingfeeds.com>